## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2175-swen-261-03-c CrispyCantaloupes
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | E.W. 3/3/18
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. | Pass | E.W. 3/3/18
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. | Pass | E.W. 3/3/18
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) | Pass | E.W. 3/3/18, 4:50pm test fails, allows double quote ' " ' in name E.W. 3/3/18, 5:20pm test passes, rejects names w/ double quote
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. | Pass | E.W. 3/3/18, 4:50pm test fails, allows duplicate names E.W. 3/3/18, 5:20pm test passes, rejects duplicate names
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. | Pass | E.W. 3/3/18
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. | Pass | E.W. 3/3/18
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | E.W. 3/3/18
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | E.W. 3/3/18
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | EW 3/4/18
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | EW 3/4/18
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | EW 3/4/18 12:45pm doesn't return to home page, 500 Internal Server Error EW 3/4/18 4:30pm Fixed, passes test
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | EW 3/4/18
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | EW 3/4/18
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | EW 3/4/18
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | EW 3/4/18
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | EW 3/4/18
As a Player I want to make a simple move so that I can move a piece on to a vacant dark square. | Given that it is my turn when I click a piece of my opponent's color then I will be notified I cannot move that piece and to try again.
Given that it is my turn when I click a piece of my color to move then the piece gets selected/highlighted
Given that I have selected a piece of my color when I click that same piece again then the piece will be unselected/unhighlighted.
Given that I have selected a piece of my color when I click another one of my pieces then the first piece will be deselected/un-highlighted and the new piece will be selected/highlighted
Given that I have selected a piece of my color when I click one of my opponent's pieces then I will be notified that the move is invalid and the piece remains highlighted on its original square.
Given that I have selected a piece of my color when I click a vacant square that is a valid simple move then the piece will be moved to that new square.
Given that I have selected a piece of my color when I click a vacant square that is an invalid move then I will be notified that the move is invalid and the piece remains highlighted on its original square.
As a Player I want to make a single jump move so that I can capture an opponent piece. | Given that it is my turn to make a move, when I move my piece diagonally forward (either to the left or right) to an empty space "jumping" over an opponent's piece, I expect my piece to land on the empty space and my opponent's piece which I "jumped over" to disappear.
Given that it is my turn to make a move, when I move my king piece diagonally forward or backward (either to the left or right) to an empty space "jumping" over an opponent's piece, I expect my piece to land on the empty space and my opponent's piece which I "jumped over" to disappear.
As a Player when I or my opponent make a legal checkers move, I want the board to update so the game can progress. | Given that it is your turn to make a move, when you move your piece diagonally forward (towards the opponent), then your move is a valid move.
Given that it is your turn to make a move, when a piece makes a non-capturing move (moves that don't involve a jump), then you expect the piece move only one square (diagonally).
Given that it is your turn, when a piece is open to be captured, then you must capture (jump over diagonally) the piece (which is then removed from the board).
Given that it is your turn to make a move, when you have more than one jump move available, then you may choose which jump to take.
Given that it is your turn, when you can jump multiple opponent pieces and select the farther empty square, then you will capture all of the jumped pieces.
Given that you have a king piece when you decide to move the king piece diagonally backward, then you expect it to be a valid move.
As a Player I want to make a multiple jump move so that I can capture several opponent pieces. | Given that it is my turn to make a move, when I make a simple jump move and there are more jump moves available for the same piece, I expect it to still be my turn allowing me to make a successive jump move.
Given that I just made a simple jump move with a piece and the same piece has more jump moves available, when I make a successive jump move with the same piece, I expect the opponent's piece I just jumped over to be removed from the board.
As a Player I want to move my king piece diagonally away or towards myself so that I can use my king piece. | Given that it is my turn and my piece is king, when I do a simple move on this piece, it is a valid move.
Given that it is my turn and my piece is a king, when I move my piece in a backwards direction by one column unit and the space is an empty space, I expect my piece to land in that space.
Given that it is my turn, when I move my king piece diagonally backward to an empty space jumping over my opponent's piece, then I expect my king piece to land in the empty spot and the opponent's piece I just captured to be removed from the board.
Given that it is my turn, when I make a jump move in the forward or backward direction with my king piece and the very king piece has more jump moves available in either the forward or backward direction or both, I expect it to still be my turn and I'm able to make successive jump moves with my king piece
As a Player, I expect to take turns with my opponent so that the game can progress. | Given that it is my turn to make a move, when I make a simple move, then I expect my opponent to be able to make the next move
Given that it is my turn to make a move, when I make a simple jump move and the very piece I just made the jump move with still has available jump moves, I expect the game to allow me to make these moves until I run out of jump moves.
As a Player, when one of my pieces jumps over one or more of my opponent’s pieces, I want the captured pieces to be removed from the game board so that I’m closer to victory. | Given that it is my turn with a valid jump move, when I jump over an opponent's piece, then i expect that opponent's piece to disappear from the board.
Given that it is my turn and I just made a jump move, if the same piece still has available jump moves, when I make a jump move and this point, I expect the piece i just captured to be removed from the board.